{{ PROJECT_CODE }} Lessons Learned

{{ COVER_DATE }}

| Project Name | Albemarle KMC Logistics Study |
| --- | --- |
| Project Code | RI.1949 |
| Project Manager | Bryan Moore |
| Date | 2026/06/09 |

Project Team

Table 1: Project Team

| Project Team | Position |
| --- | --- |
| Andre Naude (BSC) | Project Partner |
| Bryan Moore (BSC) | Engagement Lead |
| Dolfus Negunda (BSC) | Simulation Consultant |
| Matthew Verbeek (BSC) | Business Consultant |
| Levi Quelland (Albemarle) | Project Engineer |
| Shub Verma (Albemarle) | Engineering Director |
| Brayden Beaver (Albemarle) | Mechanical Project Engineer |

Deliverables

The list of deliverables set out in the Proposal are listed in the following table.

| Document | Status |  | Notes |
| --- | --- | --- | --- |
| Signed-Off Scope of Work Document | ✔ Delivered | Scope of Work signed and issued 9 February 2026, defining model boundaries, data requirements, scenario framework and cost modelling approach. |  |
| Validated Outbound Logistics Simulation Model | ✔ Delivered | Full end-to-end DES model built in WITNESS, covering KMC stockpile, rail loadout, rail transit, port receival/storage, and vessel loading/dispatch across all five port allocation strategies. |  |
| Simulation Validation Report | ✔ Delivered | Formal validation report documenting rate, availability, utilisation, throughput, and buffering validation results. Model confirmed reliable for decision-making prior to analysis phase. |  |
| Sprint 1 Results Presentation | ✔ Delivered | Presented 10 March 2026. Covered baseline Monte Carlo analysis, convergence testing, five-strategy port allocation comparison, and broad sensitivity screening across 36 parameters. |  |
| Sprint 2 Results Presentation | ✔ Delivered | Presented 24 March 2026. Introduced vessel cancellation logic, port congestion, aggressive port downtimes, reduced KMC operating hours, and half unit train scenarios. Cost model also previewed. |  |
| Sprint 3 Results Presentation | ✔ Delivered | Presented 9 April 2026. Integrated cost and working capital comparison across strategies. Completed stockpile capacity optimisation and dispatch logic hypothesis testing. Narrowed strategic options to MH100 and MH67/CC33. |  |
| Sprint 4 Results Presentation | ✔ Delivered | Presented 30 April 2026. Quantified minimum viable wagon lease requirements by strategy, finalised stockpile optimisation, completed vessel parcel size and dispatch logic what-if testing, and confirmed final recommendations. |  |
| Sprint 5 Results Presentation | ✔ Delivered | WITNESS model updated to reflect direct rail delivery from KMC to Tesla's railyard at/near Corpus Christi. Unloading by Tesla; no Tesla-side stockpiling modelled. WITNESS model updated to reflect Morehead City → OGV → Corpus Christi port → Tesla delivery pathway. Full ocean leg logistics modelled. Baseline Monte Carlo analyses for both Tesla scenario sets (all 5 tonnage splits each). No sensitivity, what-if, or optimisation runs in scope. |  |
| Final Insights Report | ✔ Delivered | Simulation Insights Report issued 1 June 2026. Comprehensive document covering methodology, validated assumptions, full scenario analysis, cost and risk findings, and strategic recommendations. |  |
| Final Executive Results & Recommendations Presentation | ✔ Delivered | Consolidated executive presentation issued 1 June 2026. Covers study scope, decision framework, strategy comparison, recommended operating designs and strategic recommendations with future opportunities. |  |

Commentary on Project Execution

Positives

| Title | Comment |
| --- | --- |
| Ideal Client Relationship | - Strong pre-existing relationships with Levi and Shub. - Client consistently helpful and supportive despite data limitations. - No relationship friction – an ideal client engagement. |
| Simulation Workflow Engineering | - Dolfus built templatised workflows for scenario creation, Monte Carlo execution, sensitivity analysis, and data migration. - CSV-to-database migration workflow saved a lot of time and effort. - Workflow blueprint is reusable and should be adopted as standard for future Witness simulation engagements. |
| Dolfus Negunda – Technical Delivery | - Rapid and effective upskilling in WITNESS. - Delivered a well-structured, reliable simulation model. - Templatised modular design is reusable for future logistics engagements. - Spending time in planning and design saved a lot of time when it came to model updates and new scenarios, allows for faster turnaround time |
| Iterative Sprint Delivery Model | - Four-sprint structure enabled actionable insight delivery at each stage. - Adaptive reprioritisation between sprints kept the analysis focused on what mattered most. - This enables better alignment and also allows them to see where they had wrong assumptions or missing gaps in what outputs they are looking for. |
| Client-Driven Scenario Ideation | - Albemarle actively contributed to scenario ideation during sprint reviews. - Client introduced the wagon leasing limit question — a cornerstone of the final recommendations. - Strong client buy-in to the analytical direction throughout. |
| Cost Model Architecture | - Standalone VDT cost model linked to simulation outputs. - Allowed rapid cost updates as scenarios changed. - Clean, auditable cost-per-ton and working capital framework. |
| Scope Pivot Handled Professionally | - Client's commercial team identified during the final presentation that CC had been modelled as an export port — a misunderstanding in the original scope. - BSC responded constructively: a formal change note was prepared and signed within 4 days of the issue being raised. - The pivot to Tesla scenarios was managed without relationship damage and with full client confidence maintained. |
| Matt’s Rapid Onboarding and Delivery | - Matthew joined the project with 2 weeks to the hard deadline. - Successfully onboarded, understood the scope pivot, and delivered the Rev 2.0 report and updated presentation on time. - Demonstrates BSC's ability to flex team composition at short notice to meet tight deadlines. - Having Matt helped ease the pressure and helped guide a more comprehensive report and nice standardised visualisations |
| Bryan and Dolf GOAT Documentation | - Onboard was made easy for Matt as both Dolfus and Bryan had made good effort to collate and produce on-boarding documentation that was ready and waiting from Day 1. - Also Dolfus and Bryan were patient and made time to answer silly questions from Matt as he tried to figure out his left from his right. |
| Model and Results Ownership | - Having Dolfus be the direct owner of the simulation allowed Matt to purely focus on result generation and documentation. |
| Experience matters | - Bryan helped guide and bridge the gap on context specifics within the scope of work - With Bryan handling the presentations he was able to engage the clients to be more interactive which led to refined simulations - Weekly reporting frameworks were well documented and neatly designed for client deliverables |
| Effective collaboration | - There has been good collaboration throughout the project, work was shared were necessary and allowed for deadlines to be met |

Challenges

| Title | Comment |
| --- | --- |
| Consultant Seniority Mix | - No dedicated business consultant on the project meant a lot of the results documentation and presentation work fell on the EL. - A mid-level business consultant alongside the simulation specialist would have balanced the load better. |
| Sprint Review Attendance Declined Late in Project | - Later sprint reviews were less well attended by the Albemarle team. - Did not materially impact delivery but is a pattern worth managing proactively in future projects. - Lack of client representation delays the identification of critical issues relevant to deliverables |
| Data Gaps at Project Start | - Port congestion, rail transit delays, vessel chartering, and port downtime parameters all had to be estimated (desktop research). - Inherent to a feasibility-stage project but created early model uncertainty. - Sprint 1 results required significant caveating as a result. |
| Cost Data Reliance on Desktop Research | - Rail freight, railcar lease, vessel charter, demurrage, and insurance costs based on BSC benchmarking. - Absolute cost figures carry uncertainty as a result. - Confirmed commercial inputs from the client were not available. |
| Hidden Buffering in Wagons-in-Transit | - Unrestricted dispatch logic allowed material to accumulate in transit. - Masked true system sensitivity — lean stockpile configurations appeared more viable than they were. - Required a dedicated hypothesis-testing analysis to identify and correct. |
| Corpus Christi Modelled as Export Port –Misunderstanding | - CC was modelled as an export port throughout the original study; Shub clarified during the final presentation that this was never the intention. - All CC-as-port findings from Rev 1.0 are superseded. - This required a 2-week extension (AUD 33,000) and a full rework of the scenario set. - This also led to key findings being discarded |
| Hard Deadline Created Delivery Pressure | - Levi Quelland confirmed June 1 as a hard deadline (leadership presentation already scheduled) when BSC's initial estimate was June 5. - The 2-week extension window was extremely tight for model updates, Monte Carlo runs, and full report revision. - Required pulling in an additional consultant (Matthew Verbeek) at short notice to meet the deadline. |
| Extension Scope Excluded Sensitivity and What-If Analyses | - The tight timeline meant the extension was limited to baseline Monte Carlo only — no sensitivity, what-if, or optimisation runs for the Tesla scenarios. - This is a limitation of the final deliverable that Albemarle should be aware of when using the results for decision-making. - Future extensions of this type should build in at least one additional week to allow sensitivity analysis. |
| Albemarle Lacked SME Feedback | - Very few of the cost assumptions were openly interrogated or confirmed by Albemarle. Affects confidence in results. |
| Results Blind Spot | - Similar to above, in the final presentation (V2), Shub communicated how he wanted to see the impact of operational drivers though a sensitivity analysis. - However Initial extension was scoped without giving time for that analysis. - This comes down to Albemarle not communicating their expected outcomes in full or not internally aligning on the outputs the simulation can provide and prioritising these before signing off on the extension. - A learning from this is perhaps either forcing an additional week to the timeline (even if it is post-deadline) or somehow illustrating exactly the type of information they will lose out on. As sensitivity analysis is often the biggest benefit with DES projects. |
| Client Did Not Fully Understand Extension Trade-Offs | - Even though the change note spelled out what was excluded, Shub likely approved the extension based on time and cost without fully absorbing what analyses would be dropped. - He only raised his desire for operational driver / sensitivity analysis at the final presentation – after the extension was complete. - The team should have more explicitly walked the key stakeholder through the specific outputs that would be lost, not just the scope inclusions |

Learnings and Suggestions

| Title | Learnings / Suggestions/ Actions |
| --- | --- |
| Adopt the Workflow Blueprint as BSC Standard | - Document and package the scenario creation, Monte Carlo, and CSV-to-database migration workflows. - Maintain templatised WITNESS modules as a reusable starting point for bulk commodity logistics models. - Target: reduce model configuration time on future logistics engagements. |
| Staff a Business Consultant on Sim Projects | - Include a business consultant to own results docs and presentations. - Allows the simulation specialist to focus on technical delivery. - Reduces EL burden and improves quality of client-facing outputs. |
| Formalise Data Request and Gap Resolution at Scoping | - Issue a structured data request register at scoping and track through to model configuration. - Formally document and agree placeholder assumptions with the client. - Flag assumptions for update as data matures. - Request key data owner in the early stages to drive input validations on assumptions and rfis |
| Enforce a Single Unit Convention at Kick-Off | - Agree metric tonne or short ton at project kick-off and enforce across all documents. - Convert client data at intake and document the conversion. - Eliminates a persistent source of inconsistency and client confusion. |
| Flexible Resourcing Model Works – Document and Repeat | - Bringing in Matt at short notice for the reporting phase of the extension worked well and allowed the team to meet the hard deadline. - BSC should consider a "flexible reporting consultant" model for simulation projects: a consultant who can be onboarded quickly to own documentation and presentation delivery in the final sprint. - The onboarding materials developed for this project (agent-assisted briefing, structured comprehension checks) should be retained as a template for future rapid onboardings. |
| Getting the Most Out of AI | - Use AI agents to maintain a living decision log throughout the project – not just for documentation at the end. Feed agents with meeting recordings, brain dumps, and key documents so they can answer "why did we decide X?" months later. - Maintain agents through dynamic context rather than editing system prompts. Invest time upfront in the system prompt; store evolving project decisions in dynamic context for easier maintenance. - Implement a weekly agent review routine: the agent reads out current decisions and to-dos; the team explicitly confirms what remains valid and what has changed. This prevents stale decisions from persisting. - Connect agents directly to project databases – a high-value capability for future simulation projects that enables seamless movement between data querying and business discussion. |
| Keep Operational Sim and Cost Model Separate | - Keep the operational simulation model and the cost model as separate, linked tools – do not embed costing directly in WITNESS. - When assumptions change late in a project, costs can be recalculated without rerunning the full simulation, saving significant time. - This separation also keeps the cost model auditable and client-readable. |
| Be More Assertive with Client Obligations | - The team should be more direct when client obligations are not being met. - This applies to: attendance from key stakeholders, data provision timelines and assumption sign-off. - Proposals already include SME time requirements; in practice, teams hesitate to enforce them. - Future projects should enforce these expectations more consistently, especially when key stakeholders are identified as critical to the analytical direction. |
| Identify Client-Side Data Owner | - Someone to take responsibility for inputs. - The earlier you can get input assumptions out, the better. |
| Benchmarking Library | - Build a library of non-time-specific validated metrics from previous projects (equipment rates, logistics parameters, cost benchmarks) so the team has a reliable internal reference. - BSC likely has sufficient historical mining and logistics data to populate many categories. This reduces reliance on desktop research and improves assumption quality from day one. - The idea has been discussed at senior levels before – it requires investment and clear value recognition to get off the ground. |
| Present the Change Note to the “Shub” of the project | - When a scope change or extension is negotiated, do not rely solely on the project manager (e.g. Levi) to cascade the implications to the technical team. - Present the change note directly to the key technical stakeholder (e.g. Shub). - Confirm explicitly what outputs and analyses will and will not be delivered. - This prevents late-stage surprises where a stakeholder raises requirements that were already descoped. |
| Educate Clients on How Iterative DES Modelling Works | - Clients often assume that once the model is built, it should immediately produce accurate results. - Budget time early in the project to give clients a brief orientation on the modelling process: early results are preliminary, heavily assumption-dependent, and intended to close information gaps through iterative review sessions. - Results improve asymptotically toward a robust answer. - Setting this expectation upfront reduces friction and improves the quality of client feedback during sprint reviews. |